## Sheet1
Risk Assessment
Risk ID | Risk Description | Risk Outcome | Potential Impact | Likelihood | Mitigation needed? | Action taken
| Cross Site Request Forgery (CSRF) attack | An unauthorised command is executed on the webpage to modify or delete user information | User information may be modified or deleted from the database, disallowing users to access their accounts | Low | Yes | CSRF protection was added with use of a secret key
| Site overload | A large amount of users may be attempting to access the webpage may cause the servers to become overloaded. | The webpage may become unavailable for a long period of time. | Low | Yes | A production server was created using Gunicorn, where a number of workers can be increased to compensate for increased traffic. A swarm of nodes with several duplicates of the containers were included to handle larger amounts of traffic.
| Site overload (Mitigated) | A large amount of users may be attempting to access the webpage may cause the servers to become overloaded. | With the previously discussed mitigation, the likelihood of this happening has decreased significantly. | Very Low | No | The mitigation has decreased the likelihood of this event significantly and the resources currently available do not allow for an increase to the mitigation.
| Procurement of equipment | There may be some form of obstruction that will delay in the gathering of required resources | Equipment necessary for the creation and running of the web application may not be available when required. | Medium | Yes | Alternative technologies were investigated that would allow for similar or identical results to be achieved.
| Procurement of equipment (Mitigated) | There may be some form of obstruction that will delay in the gathering of required resources | Research of alternative equipment and technologies ensure that a backup will always be available for a downage anywhere within the system. | Very Low | No | Research has been completed to ensure that no gaps in the equipment chain will be present
| Server downage | The server may become inactive due to intentional or accidental damage. | The webpage will become inactive, not allowing for users to access the webpage and its features. | Low | No | Server is managed by third-party.